{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":51,"n_cols":12,"rows_kept":51,"merged":[[0,0,0,11],[1,0,1,11],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,2,7],[2,8,3,8],[2,9,3,9],[2,10,3,10],[2,11,3,11],[4,1,7,1],[8,1,11,1],[13,1,15,1],[17,1,19,1],[17,7,19,7],[17,8,19,8],[17,9,19,9],[17,10,19,10],[17,11,19,11],[20,1,21,1],[23,1,25,1],[23,7,25,7],[23,8,25,8],[23,9,25,9],[23,10,25,10],[23,11,25,11],[26,0,27,0],[26,1,27,1],[26,2,27,2],[26,3,27,3],[26,4,27,4],[26,5,27,5],[26,6,27,6],[26,7,27,7],[26,8,27,8],[26,9,27,9],[26,10,27,10],[26,11,27,11],[31,1,32,1]],"flags":["formulas_cached_only"]}
["2010年8月份安居公司建设项目进展情况表"]
["                                                                                                                                                    2010-8-26"]
["序号","小区名称","项目名称","完成投资情况",{"$nulls":4},"已完成工作","存在问题","解决问题的建议","下一步计划"]
[{"$nulls":3},"总投资（万元）","本月完成投资（万元）","2010年计划完成投资（万元）","至2009年累计完成投资（万元）","2010年累计完成投资（万元）"]
[1,"龙祥小区","龙祥小区廉租房",3430,41,936,486.74,514.51,"内外墙粉刷","钢丝网与墙体大姐部分长度不够，顶转填塞不密实","及时要求整改","外墙粉刷，贴面砖及塑钢窗安装"]
[2,null,"龙祥小区经济适用房",4569,56,1279,668.83,720.92,"内外墙粉刷","钢丝网与墙体大姐部分长度不够，顶转填塞不密实","及时要求整改","外墙贴面砖及塑钢窗安装"]
[3,null,"龙祥小区安置房",5186,64,1378,752.65,662.48,"内外墙粉刷","4#楼进度偏慢，砌体工程顶转部分填塞不密实","合理安排，加快进度；对于存在问题及时整改","外墙粉刷及外墙面砖铺贴"]
[4,null,"工业学校安置房",2393,100,900,20,370,"完成8-11层梁、板砼浇捣","无","无","完成12-14层梁、板砼浇捣"]
[5,"谢洋小区","谢洋廉租房一期",5890.4,112.35,1374,1377.7,687.06,"1#-3#楼已完工，正办理验收手续；4#楼完成16-屋面板砼浇捣，砌体11-14层；5#楼完成16-屋面板砼浇捣，砌体至9-13层","无","无","4#、5#楼完成砌体，内部水电预埋管线施工及内外墙粉刷工作"]
[6,null,"谢洋廉租房二期",6674.8,190,1557,1651.26,987.43,"4#楼完成16-屋面板砼浇捣，砌体11-14层；5#楼完成16-屋面板砼浇捣，砌体至9-13层；6#楼完成13-15层梁、板砼浇捣，砌体2-5层","无","无","4#、5#楼完成砌体，内部水电预埋管线施工及内外墙粉刷工作；6#楼完成16-屋面板砼浇捣，砌体至6-12层"]
[7,null,"谢洋廉租房三期",858.4,22.65,200,239.55,93.82,"6#楼完成13-15层梁、板砼浇捣，砌体2-5层","无","无","6#楼完成16-屋面板砼浇捣，砌体至6-12层"]
[8,null,"谢洋经济适用房",1376.4,60,321,380.7,132.3,"7#主体施工至3-6层梁、板砼浇捣","无","无","7#楼完成至7-10层梁、板砼浇捣"]
[9,"莲东新区B地块","莲东新区B地块安置房",129610.8,0,{"$nulls":3},"征地已完成，拆迁完成90%","村委瓮金朝说村部有部分产权属于他，现村长要求翁金朝提供证据，才给予盖章确认","请南城陈胜周帮忙协调","尽快将村部拆迁协议签订完"]
[10,"莲东新区C地块","莲东新区C地块廉租房",6121,51,1300,4823,562,"1#-3#楼室外进行绿化施工；4#-6#楼主体施工至15-17层楼板浇捣及水电预埋，砌体5-13层","无","无","完成1#-3#楼绿化施工，并组织各分部、各专项验收；4#-6#楼主体封顶、屋面构架、砌体"]
[11,null,"莲东新区C地块经济适用房",7167,164,3000,2660,1726,"4#-6#楼主体施工至15-17层楼板浇捣及水电预埋，砌体5-13层","无","无","4#-6#楼主体封顶、屋面构架、砌体"]
[12,null,"莲东新区C地块安置房",834,45,359,309,83,"完成2-4层梁板混凝土浇捣及水电预埋","无","无","主体封顶、屋面构架的混凝土浇捣及水电预埋"]
[13,"莲东新区D、E地块","莲东新区D、E地块",null,9,{"$nulls":3},"青苗补偿完成99%","邱炳坤户拆迁未协调好","已将材料送往房管局拆迁科申请裁决","进一步协商并等待裁决受理"]
[14,"莲东新区F地块","莲东新区F地块经济适用房",null,0,null,null,28.29,"按初步设计会议中专家提出的意见对图纸进行修改优化","原立项为安置房，现小区设计有安置房、经济适用房、高级人才公寓","从该项目的可行性研究报告开始，变更办理相关手续，保障性手续变更办理应由专人负责办理","完成初步设计；待交地后，勘察单位进场"]
[15,null,"莲东新区F地块安置房",null,0]
[16,null,"限价房",null,0]
[17,"金鸡小区一期","金鸡小区A地块安置房",null,0,null,103,null,"已基本完成前期工作及房屋入户测量、房屋面积核对；东侧的初步设计工作，西侧设计工作由厦门天厦设计公司中标，方案进行中","在房屋入户测量工作中，抢建之风严重；七户强拆问题，征地补偿标准不一致","抢建之风严重，希望镇、城建等相关执法部门监督并制止；在征地补偿标准上，我司人员和村两委共同协商，请村两委给予解决","继续征地拆迁工作；及时办理面积增大相关总平、红线、用地手续；完成西侧的单体方案的设计，并提交规划局审批"]
[18,null,"金鸡小区C地块廉租房",7000,92.6,1200,400,709.6,"完成了土方开挖及基坑支护，主体施工标招标，并完成红线一栋民房的拆迁工作","在房屋入户测量工作中，抢建之风严重；七户强拆问题，征地补偿标准不一致；红线内临时搭盖影响2#楼的施工，及临时道路征地未到位无法通行，将影响材料设备的进场","抢建之风严重，希望镇、城建等相关执法部门监督并制止；在征地补偿标准上，我司人员和村两委共同协商，请村两委给予解决","进行土洞处理，办理施工许可证，组织施工队进场施工"]
[19,"金鸡小区二期","金鸡小区B地块安置房",37577,150,null,105,200,"已基本完成前期工作及房屋入户测量、房屋面积核对；东侧的初步设计工作，西侧设计工作由厦门天厦设计公司中标，方案进行中","在房屋入户测量工作中，抢建之风严重；七户强拆问题，征地补偿标准不一致","抢建之风严重，希望镇、城建等相关执法部门监督并制止；在征地补偿标准上，我司人员和村两委共同协商，请村两委给予解决","继续征地拆迁工作；及时办理面积增大相关总平、红线、用地手续；完成西侧的单体方案的设计，并提交规划局审批"]
[20,"南芳小区","南芳小区廉租房",6539,0,null,null,64,"前期工作已基本完成，入户测量已完成65%","总平面图、户型图未完成","建议规委会尽快审核通过总平图及户型图；征地资金应尽快到位","进一步与镇、村干部协商，争取尽快完成征地拆迁工作"]
[21,null,"南芳小区经济适用房",69198,0]
[22,null,"南芳小区安置房",66228,0]
[23,"南芳小区二期（友邦小区）","南芳小区二期（友邦小区）",32949.7,0,null,null,7,"已完成规划红线图和建设用地规划许可证，已摇号机选抽取方式编制可研、环评、地灾；申请用地指标","土地分区规划图中，规划局与国土局的土地分类图有出入，土地性质未确定","尽快与规划局、国土局核对地类图，确定分区规划出图","土地预审，以及相关可研、地灾、环评工作"]
[]
[24,"龙岩学院青年教师周转房","龙岩学院青年教师周转房",2466.8,14,0,0,83.34,"项目红线图，规划许可证，总平，地灾，可研，环评，土地预审，立项；施工临时彩钢板围墙已做好，完成初勘，活动房搭设完毕","由于供地内的高压线杆用铝线，为了今后施工方便和安全考虑，将高压线杆移开成埋地","尽快解决处理","通电，相关手续的办理，设计、监理、施工招标"]
[25,"小洋保障性住房","小洋保障性住房",null,0,0,0,0,"项目红线图，规划许可证，总平，地灾，环评","由于项目进行过坐标调整（54转80），相关材料需变动","检测需调整的手续，补足资料","土地预审、立项工作"]
[26,"龙辉小区","龙辉小区保障性住房",50792.93,0,null,0,600,"完成项目红线，总平及审查意见，土地预审，立项，农用地转用手续","无","无","农用地转用手续已在公告阶段，待文件下达后准备供地手续"]
[27,"桃源小区","桃源小区一期",20820,488.23,4500,9965.76,2342.87,"外架拆除，门窗安装等","供电表设计未完，电表箱无法安装","建议公司出面协调","完成1-3#楼楼梯扶手，铝合金窗扇安装，内墙抹灰"]
[28,null,"桃源小区二期",17743,259.81,7000,4572.63,3208.69,"7#-9#楼完成至9层主体，北侧土方回填","无","无","完成10-12层主体"]
[29,"莲庄小区","莲庄小区安置房",83600,0,null,null,702.6,"土地预审、立项、报批送审","国土局用地科经办人程序不熟练，速度较慢","无","报批总平；扩大部分设计招标；待总平报批后，进行初步设计；办理供地手续"]
[30,"莲花湖安置（西洋）小区","莲花湖安置（西洋）小区",950705,0,0,0,0,"完成项目建议书，正进行规划红线等前期工作","规划设计院提出：该项目用地范围需调整，因为西环路和犀牛路规划还未定，所以规划范围需暂缓","无","完成规划红线和总控规图，办理土地预审等工作"]
[31,"龙盛小区","龙盛安置小区",111023.1,0,{"$nulls":3},"前期工作基本完成，正在办理拆迁许可证","市房管局要求增加风险评估和社会调查两项资料","征求房管局拆迁科意见，尽快准备好风险评估和社会调查两项资料","主要准备好风险评估和社会调查两项资料，同时进行部分征地工作"]
[32,"龙发小区","龙发小区安置房",91373.8,0,null,null,289,"已完成项目预审、立项、报批农用地转用手续、总平及审查","无","无","农用地转用手续已在公告阶段，待文件下达后准备供地手续"]
[33,"龙昌小区","龙昌小区安置房",44080,0,1000,0,1.73,"已完成可研、环评、地灾、土地预审、立项","大洋村委会提出现行解决该小区沿街店面所有权问题，否则不同意在《征地告知书》上盖章","与村委及相关部门沟通协商解决","办理农用地转用手续"]
[34,"龙泉小区","龙泉小区安置房",30139.6,0,0,0,0,"项目红线图修改已获得领导同意，等取得批示文件后到规划局划红线","区政府已把关于扩大龙泉小区建设规模的请示发文到市政府，但市政府未予回复","无","进行规划更改"]
[35,"紫博小区（浮东路安置小区）","紫博小区（浮东路安置小区）",52000,0,0,0,0,"已摇号机选抽取方式编制可研、环评、地灾，项目的规划选址工作","该项目的土地性质正在调整，规划部门对项目的审批工作还未完成","无","委托地灾、环评、可研、土地勘察等工作"]
[36,"西安金融小区","西安金融小区安置房",31115,0,null,null,50,"已完成设计招标工作，正在进行总平户型调整","规划要求结合龙岩大道安置房统筹安排","无","准备报方案审批"]
[37,"小洋新城","小洋新城安置房",53000,20,2000,0,620,"完成葫芦溪改河工程","一期工程及坊工程准备开工，部分位置拆迁未协调解决","建议请拆迁公司协调解决","一期图纸进行审查"]
[38,"莲塘小区","莲塘小区安置房",131818,4.2,null,null,95.7,"已完成控规图、总平图审查、红线图、建设用地规划许可证、项目建议书批复、土地预审、地灾评估案、环评批复、立项批复；供地办理中","初步设计批复未完成","无","办理供地手续、初步设计批复"]
[39,"兴业路","兴业路",null,0,0,0,0,"正进行方案设计","经现场摸底，该项目拆迁面积估算约2万㎡，从福三线到收费处有林地约29亩，其中涉及到曹溪镇浮蔡村和东肖镇洋潭村的21、22组，地形较复杂；高压线也需迁移","项目涉及到林地，需等到林地预审和批复工作完成后才可以办理立项手续","跟踪项目方案设计批复，委托可研、环评、地灾、水土保持方案等工作"]
[40,"莲南路二期","莲南路二期A段",910,0,null,630,300,"基本完成工程扫尾工作","无","无","工程初步验收"]
[41,"九一路停车楼","九一路停车楼",1731,50,750,800,518,"1、完成北区升降横移车库的安装工作（包括消防工程），完成地下室1-7轴的地面工程                                          2、南区停车设备安装完成50%","无","无","计划9月底完成主体工程单体竣工验收工作,完成南区车库的安装及调试工作，完成北区车库的验收工作"]
[42,"商务板块配套工程","商务板块配套工程","约900",0,null,0,0,"正进行设计委托","正落实各主体单位设计合同中是否包含配套设计内容","无","继续落实设计是否单体委托并开始进行设计"]
[43,"曹溪美苑","曹溪美苑",26055,0.15,null,0,0.15,"正在办理土地预审","地灾中介公司内部衔接不清楚，报告未完成","无","土地预审"]
[44,"“110”指挥中心安置房","“110”指挥中心安置房",1404,0,200,803,202,"1、完成绿化验收工作，完成规划验收工作 2、已基本做好小区外道路及排水沟改造工程的协调工作。","因小区外道路未协调清楚，小区内大门位置及绿化工作还未施做，围墙未完善","无","组织工程竣工验收会议，完成小区外道路改造工程"]
[45,"东山片区","东山片区",null,0,null,0,0,"正进行现场摸底的前期工作","该项目的用地总面积约137.1公顷，拆迁面积估算约12万㎡，农保地面积约74.2公顷，东环路到莲庄路之间、天星路以北到莲南路、天星路以南到浮东路还有约52.9公顷农保地未调，项目涉及到曹溪石粉村、曹溪东山村和董邦村","74.2公顷的农保地由市国土资源局报省厅调整","委托项目可研、地灾、环评等前期工作"]
[46,"城北片区","城北片区",null,0,null,0,0,"正进行现场摸底的前期工作","该项目的用地总面积约713.4公顷；闽西监狱预留用地面积约97.3公顷（其中监区用地面积约62.4公顷，干警生活区约34.9公顷）；需保留用地用地面积约121.3公顷；可用地含城市道路的面积约494.8公顷；拆迁建筑面积约5万㎡","67.89公顷的农保地由市国土资源局报省厅调整","委托项目可研、地灾、环评等前期工作"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}